## WBS v1
|  | AHI Real-Time Market Analytics App Project |  | Level 1 Project level
Phase 1: Planning & Foundations | Phase 2: App Development & Configuration (Agile – Scrum) |  | Phase 3: Testing, Training & Launch (Predictive + Agile QA) | Level 2 Phase level
1.1. Develop project charter and stakeholder register | 2.1. Set up development environment and create product backlog |  | 3.1. Perform internal QA and system integration testing | Level 3 Work package level
1.2. Define project approach (hybrid Agile + Predictive) | 2.2. Develop UI/UX and app navigation |  | 3.2. Conduct UAT with focus group participants
1.3. Set budget, timelines, and approval checkpoints | 2.3. Build customer segmentation and market targeting tools |  | 3.3. Execute security and compliance checks
1.4. Identify infrastructure and IT requirements | 2.4. Implement real-time analytics dashboard and data feeds |  | 3.4. Deliver staff training and user documentation
1.5. Procure IT hardware and software | 2.5. Develop secure invoicing and order processing |  | 3.5. Deploy app to production
1.6. Recruit additional IT personnel | 2.6. Conduct sprint reviews, retrospectives, and backlog refinements |  | 3.6. Monitor performance and execute project closeout