## Product Backlog
Product Backlog for Project
User Story Identifier | Priority | Category | Team | Role | Need | Value | Acceptance 1 | Acceptance 2 | Acceptance 3 | Acceptance 4 | Story Points | Comments

## Product Backlog Example
Product Backlog for Project AHI Market Analytics Mobile App Development
User Story Identifier | Priority | Category | Team | Role | Need | Value | Acceptance 1 | Acceptance 2 | Acceptance 3 | Story Points | Comments
2 | 1 | Customer | App Dev 1 | As a customer | I want secure checkout and confirmation | So I trust the platform and complete purchases | Encrypted payment processing | Receives email confirmation | Can view past orders | 2 | Sprint 1
8 | 2 | Employee | QA Team | As a QA tester | I need to verify app meets security standards | To ensure we avoid regulatory risk | Checklist for compliance tests | Test logs saved to audit trail | All test cases pass before release | 4 | Sprint 1
4 | 3 | Employee | Finance | As the finance director | I want accurate invoicing and order records | So I can track revenue and reconcile accounts | Invoice automatically generated per order | Admin panel shows order history | Secure data access with role-based controls | 3 | Sprint 1
1 | 4 | Customer | App Dev 1 | As a customer | I want to explore products by skin type | So I can quickly find what fits my needs | Filters by skin type | Shows personalized product suggestions | Highlights new and trending products | 1 | Sprint 2
5 | 5 | Employee | IT Ops | As the IT lead | I need to monitor system performance | So we can ensure uptime and responsiveness | Alerts on system errors | Logs are updated in real time | Integration status indicators | 5 | Sprint 2
3 | 6 | Employee | Marketing | As a marketing analyst | I need to track product interest in real time | To adjust promotions and campaigns quickly | Dashboard with live data feed | Reports exportable by region | Trend alerts enabled | 5 | Sprint 2
6 | 7 | Employee | Product Team | As the product owner | I want to collect user feedback on new features | So we can refine product direction | Post-feature surveys appear | Feedback form saves responses | Reports display satisfaction trends | 2 | Sprint 3
9 | 8 | Customer | App Dev 1 | As a returning customer | I want to see my order status | So I know when to expect delivery | Orders shown in profile | Status (e.g., pending, shipped) updated | Notifications via email/SMS | 2 | Sprint 3
7 | 9 | Customer | UX Research | As a focus group user | I need to try app features before launch | To give real-world usability feedback | Access to test environment | Form to log issues and suggestions | Clear tasks for each test round | 2 | Sprint 3
10 | 10 | Employee | Vendor Ops | As a vendor manager | I need our partner product list updated weekly | So listings are accurate and complete | Scheduled data sync | Alerts on failed imports | Manual override possible | 3 | Sprint 4

## Story Points Solution
1 Story Point | 2 Story Points | 3 Story Points | 4 Story Points | 5 Story Points
[5 empty] | User Story Identifier | Story Points
[5 empty] | 1 | 1
[5 empty] | 2 | 2
[5 empty] | 6 | 2
[5 empty] | 9 | 2
[5 empty] | 7 | 2
[5 empty] | 4 | 3
[5 empty] | 10 | 3
[5 empty] | 8 | 4
[5 empty] | 5 | 5
[5 empty] | 3 | 5
[5 empty] | Total Story Points | 29
Less Complex More Complex
User Story 2
User Story 1
User Story 6
User Story 7
User Story 9
User Story 4
User Story 10
User Story 8
User Story 3
User Story 5