## Sprint 1
Sprint 1 Backlog (Enable Secure Checkout And Compliance Verification) for Project AHI Market Analytics Mobile App Development
Story ID | Resource | Story/Task | Time Required (Hours) | Time Remaining (Hours)
0002 Customer Needs 1 | Lead: Cary Manning | User Story: Easy Access to Orders | 40
| Alex Chen | Task 1: Implement encrypted payment API | 12
| Rina Pater | Task 2: Build frontend checkout interface | 10
| Lena Hoffman | Task 3: Write UI tests for checkout | 8
| Cal Hamer | Task 4: Define payment flow rules | 10
0008 Employee Needs 1 | Lead: Priya Service | User Story: Compliance Testing | 35
| Lena Hoffman | Task 1: Create compliance test checklist | 8
| Priya Service | Task 2: Validate logging meets policy | 7
| Cal Hamer | Task 3: Review test coverage with QA | 5
| Jamal Brooks | Task 4: Ensure secure CI pipeline | 10
| Alex Chen | Task 5: Validate backend logging | 5
0004 Employee Needs 2 | Lead: Oscar Money | User Story: Order Visibility | 30
| Oscar Money | Task 1: Specify invoice data fields | 5
| Alex Chen | Task 2: Implement invoice generation logic | 10
| Rina Pater | Task 3: Build order history page | 10
| Jamal Brooks | Task 4: Configure access control | 5
Total Sprint Hours |  |  | 105 | 0