## Stakeholder Register v1
Stakeholder Register: AHI Real-Time Market Analytics App Project
Name | Organization | Role | R | A | C | I | Comments
Cary Manning | Marketing | Project Manager | X | X |  |  | Manages scope, schedule, and team
Mary Smithers | Marketing (Sponsor) | Sponsor |  | X | X |  | Approves scope, funding, and major decisions
Priya Service | IT | Technical Lead | X |  | X |  | Leads integration, infrastructure, and security
Ram Samuels | Marketing | Marketing Director / SME |  |  | X | X | Advises on marketing analysis capabilities
Oscar Money | Finance | Finance Director |  |  | X | X | Monitors budget and disbursements
Cal Hamer | PMO | Product Owner / VOC | X |  |  | X | Manages backlog and prioritization
Keiko Tanaka | Marketing | Core Team Member | X |  |  |  | Executes tasks related to UI/UX and testing
Jose Garcia | Marketing | Core Team Member | X |  |  |  | Customer feedback analysis and testing
Focus Group Members | Customer | End Users (External) |  |  | X |  | Provide feedback and test usability
RACI terms defined | ROLE | DEFINED |  |  |  | Version: 1, 18 June 20xx
| R | Responsible for performing work or tasks
| A | Accountable for outcomes
| C | Consult as a subject matter expert (SME)
| I | Inform as project progresses