## budget v1
High-Level Budget: Resource Breakdown Structure Project Name: Date:
WBS identifier # | Work package | Internal personnel required | External personnel required | Venue costs | Materials required | Supplies required | Equipment required | Comments | Total direct costs
1.1 | Develop project charter and stakeholder register | 1 | 0 | 0 | 100 | 50 | 0 | Led by PM | 151
1.2 | Define project approach (hybrid Agile + Predictive) | 1 | 0 | 0 | 50 | 20 | 0 | PM and Product Owner | 71
1.3 | Set budget, timelines, and approval checkpoints | 1 | 1 | 0 | 30 | 0 | 0 | PM + Finance | 32
1.4 | Identify infrastructure and IT requirements | 1 | 1 | 0 | 150 | 100 | 200 | IT and PM | 452
1.5 | Procure IT hardware and software | 0 | 1 | 0 | 200 | 50 | 500 | IT + Vendor | 751
1.6 | Recruit additional IT personnel | 1 | 0 | 0 | 0 | 0 | 0 | HR effort only | 1
2.1 | Set up dev environment + create backlog | 1 | 1 | 0 | 200 | 100 | 400 | Product Owner + IT | 702
2.2 | Develop UI/UX and app navigation | 1 | 1 | 0 | 200 | 100 | 400 | Marketing | 702
2.3 | Build customer segmentation and targeting | 1 | 1 | 0 | 250 | 150 | 600 | Marketing | 1002
2.4 | Implement real-time analytics + data feeds | 1 | 1 | 0 | 300 | 200 | 700 | IT + Marketing | 1202
2.5 | Develop secure invoicing & order processing | 1 |  | 0 | 150 | 100 | 300 | IT + Finance | 551
2.6 | Sprint reviews and backlog refinements | 1 | 0 | 0 | 100 | 80 | 0 | Product Owner | 181
3.1 | Perform internal QA & system testing | 1 | 1 | 0 | 100 | 100 | 300 | QA + IT | 502
3.2 | Conduct UAT with focus groups | 1 | 1 | 0 | 100 | 100 | 300 | Product Owner + Marketing | 502
3.3 | Execute security & compliance checks | 0 | 1 | 0 | 150 | 80 | 200 | IT + Legal | 431
3.4 | Deliver staff training & documentation | 1 | 1 | 0 | 200 | 200 | 100 | Training team | 502
3.5 | Deploy app to production | 1 | 1 | 0 | 150 | 100 | 200 | IT team | 452
3.6 | Monitor and execute project closeout | 1 | 0 | 0 | 100 | 50 | 100 | PM | 251
TOTAL COSTS |  |  |  | 0 | 2530 | 1580 | 4300 | 0 | 8438
Contingency requirements (10%) | [8 empty] | 843.8
Personnel cost requirements | [5 empty] | Note: Update cost categories to reflect actual project requirements
Rate | Name | Hours | Costs
37.5 | Cary Manning (Project Manager) | 88 | 3300
37.5 | Priya Service (IT Lead) | 48 | 1800
37.5 | Keiko Tanaka (Marketing Core Team) | 40 | 1500
62.5 | Jose Garcia (Marketing Core Team) | 40 | 2500
62.5 | Oscar Money (Finance Director) | 10 | 625
68.75 | Cal Hamer (Product Owner) | 56 | 3850
55 | Alex Chen (Backend Developer) | 60 | 3300
52 | Rina Pater (Frontend Developer) | 60 | 3120
58 | Jamal Brooks (DevOps Engineer) | 45 | 2610
50 | Lena Hoffman (QA Engineer) | 50 | 2500
TOTAL |  |  | 25105