## Quality Mgt Plan
Quality management plan for project: AHI Real-Time Market Analytics App
Part I: Project objectives (reference project charter)
1. Ensure app captures accurate market segmentation and trend data
2. Verify secure user access, data protection, and invoicing workflow
3. Develop and validate analytics dashboard and data feeds
4. Confirm app UI/UX supports smooth customer journey
5. Conduct UAT with focus group and ensure usability feedback is acted upon
6. Launch fully operational version of the app
7. Monitor app performance post-launch and report KPIs
Part II: Project quality team (Project Manager, QA, QC, SME)
Name | Role | R (Responsible) | A (Accountable) | C (Consult) | I (Inform)
Cary Manning | Project Manager | X | X
Priya Service | QA/IT Lead | X |  | X | X
Jose Garcia | QC & Marketing SME | X |  | X | X
Oscar Money | Finance SME |  |  | X | X
Cal Hamer | Product Owner | X | X
Focus Group Leader | UAT/Customer Rep | X |  |  | X
Quality assurance activities (quality audits) |  |  | Quality control activities (quality inpections)
Audit design documentation & backlog |  |  | Verify app UI/UX and navigation flow
Audit feature development sprints |  |  | Verify dashboard and analytics data accuracy
Audit testing procedures (QA + UAT) |  |  | Verify secure login, invoicing, and compliance
Audit training + deployment process |  |  | Verify training content and post-launch checklist
Audit performance & feedback post-launch |  |  | Verify metrics, usage reports, and VOC (Voice of Customer)