## Comm Mgt Plan
Communications plan template for project: AHI App Development Project
Communications item forum (What) | Owner (Who-Sender) | Audience (Who-Receiver) | Timing (When) | Format medium (How) (Where) | Purpose (Why)
Weekly Sprint Review | Cal Hamer (Product Owner) | Cary Manning, Priya Service, Jose Garcia, Keiko Tanaka | Weekly on Fridays, 3:00 PM | MS Teams / Confluence | Review progress, demo features, backlog review, gather feedback
Project Sponsor Check-In | Cary Manning | Mary Smithers (Sponsor) | Bi-weekly, Mon 10:00 AM | Zoom or Executive Office | Share status, resolve blockers, strategic updates
Stakeholder Status Report | Cary Manning | All Key Stakeholders | Every Monday by 12:00 PM | SharePoint / Email | Share current project status, delays, risks, decisions
Change Control Board (CCB) | Oscar Money | Cal Hamer, Ram Samuels, Priya Service | Monthly (2nd Tuesday) at 11:00 AM | Conference Room / Zoom | Review and approve/reject change requests
Focus Group Session Briefing | Jose Garcia | Keiko Tanaka, Cal Hamer, Vendor Rep | One-time (Before UAT) | Zoom | Prepare for UAT; align expectations
UAT Results + Feedback Debrief | Priya Service | QA Team, Product Owner, Marketing | One-time (After UAT) | Confluence / QA Debrief Channel | Review UAT findings, assign fixes, update sprint planning
App Launch Planning Sync | Cary Manning | All Departments (IT, Marketing, Finance) | One-time (Week before deployment) | Main Conference Room | Finalize deployment, comms, support plans
Version: 01 |  |  | Date: 18th June, 20xx