## Risk Register
Project: AHI Real-Time Market Analytics App – Risk Register Date: 18th June, 20xx
# | Cause (condition/situation) | Event | Impact | Risk owner | Category | Probability risk rating | Impact risk rating | Risk score | Trigger | Response
1 | Integration complexity | Incompatible APIs or data feeds | Delays in dashboard delivery | Priya Service | T | 4.5 | 4.5 | 20.25 | System test failures | Use modular design and early integration tests
2 | Limited user feedback | Unclear app usability issues | Poor customer adoption | Cal Hamer | T | 3.5 | 5 | 17.5 | Low UAT participation | Expand focus group early
3 | Data privacy regulations | Policy non-compliance | Legal penalties, relaunch costs | Oscar Money | T | 3 | 5 | 15 | Compliance audit flag | Review with legal pre-launch
4 | Internal IT capacity | Dev team stretched across priorities | Missed sprint deadlines | Priya Service | T | 4 | 4 | 16 | Missed daily scrums | Add temp IT staff or rebalance sprint scope
5 | Stakeholder misalignment | Conflict on feature priorities | Change requests + scope creep | Cary Manning | T | 3 | 4 | 12 | Delays in backlog approval | Conduct alignment workshops
6 | Customer data quality gaps | Inaccurate analytics | Poor decisions based on data | Jose Garcia | T | 2.5 | 4 | 10 | UAT data review issues | Clean data set pre-load
7 | Strong sponsor engagement | Fast escalation + support | Faster decisions, high morale | Mary Smithers | O | 5 | -5 | -25 | Immediate response to issues | Involve early in critical reviews
Total Risk Score | [7 empty] | 28 | Risk Exposure
|  | Probability risk rating |  | Impact risk rating
|  | 5: High |  | 5: High
|  | 4: High to moderate |  | 4: High to moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to low |  | 2: Moderate to low
|  | 1: Low |  | 1: Low